## Sheet1
Capstone project by ‘The Distracted’
Subsystems | Nodes | Compexity/Toughness | Number of people | Remarks
Perception | Traffic light detection | Tough | 2 | It has 2 aspects – should work well both in simulator as well as in Udacity site. People have reported using different solutions for the two.
Planning | Waypoint Loader & Updater | Easy | 1
Control | Waypoint Follower and DBW | Medium | 2 | It may need 1 person. But differnt time zones can be utilized for better productivity
Udacity discussion for the System Integration project: https://discussions.udacity.com/c/nd013-system-integration Slack channel: #p-system-integration Slack channel: #p-system-integration
Tasks | Subsystem | Details | Links
Acquiring data | Perceptiion | Deciding on what data to use. Surveying the existing literature and work
Tensor Flow setup on a GPU | Perceptiion | Creating an AMI. Setting & sharing the guideline for its use. Instances are costly
Designing the CNN model | Perceptiion | Adopting from existing model is best. Transfer learning could be explored. Also the model should not be too heavy for performance reasons. | Great Udacity discussions on the same: https://discussions.udacity.com/t/survey-traffic-lights/342249/31 https://discussions.udacity.com/t/labeling-images-for-classification/414072/14 Tensor Flow relevant links: Image retraining: https://www.tensorflow.org/tutorials/image_retraining Object Detector API: https://towardsdatascience.com/how-to-train-your-own-object-detector-with-tensorflows-object-detector-api-bec72ecfe1d9
Training/Testing for simulator | Perceptiion
Training/Testing for Carla | Perceptiion
API packaging | Perceptiion | Test its able to publish on ROS channels
Stub to test locally | Perceptiion | A local dummy, which can publish on channels in a hard coded way. So that we can test car stopping properly at signals.
Development and testing platform | All | Since we need some GPUs which are typically not available locally. We need to use an p2 instance and setup an AMI, with appropriate software.
Updater (partial) | Planning | This should happen as early as possible. So that the team can try it out locally with their simulators
Updater (full) | Planning | This will at least need the dummy/stub of Perception Subsystem. So can happen in the second week.
PID controller | Control | The PID constants using Twiddle/etc